| Contract no: | SCM-668935 |  | Contract name: | Lower Street |  | Date: | 08.08.19 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Written by: | Darren Tugwell |  | Weather AM: | Cloud with sunshine |  | Temp. at time of visit (°C): | 22 |
| Section: (if applicable) | N/A |  | Weather PM: | Some light rain |  |  |  |
| Photos taken: | Yes | Y | My time onsite | 11:20 | My time offsite |  |  |
|  | No |  |  |  |  |  |  |

| Works conducted/labour |  |  |
| --- | --- | --- |
| Company name: | Labour (No): | Details: |
| R&W | 1x site Foreman, Dave Eskriett 3x operatives 3x TM operatives 1x vac ex operator | Site setup, Additional diversion signs and road ahead signs have been put in place, most of the diversion signs with movable arrows have been replaced with ones that don’t move as requested by the local council. Plant, Vac-ex is onsite this should be the last day for this. Works taken place, Excavation for gully and new chamber that will lead to the garages have taken place, the excavation for the chamber is approximately 1.6mtr deep, I have asked to the excavation to be made about 1.5mtr wider and for it to be stepped to reduce the risk of the sides collapsing. We think that we amy have found a location for the chamber that will connect the drainage run from across the road, this will hopefully be next to the existing kerbs, in failing that we may have to incorporate some of the existing services into the new chamber. Old pipe run that is surrounded by bricks is being removed to make way for new 225mm pipe. Some materials to be obtained tomorrow (Friday) and hopefully the chambers will start to be installed. |

Instructions given to subcontractors

Instructions received from the client

N/A

Traffic Management Onsite

Road closure, 2x gateman with a vehicle each of the closure.

Subcontractor commercial notes: (Any delays, issues, possible contra charges, notable events)

Materials should start to be collected tomorrow, a VO will be required for these.

Detail any materials and Kier plant or equipment (check Contract for definition, the machinery used to construct the work is called “equipment” on some Contracts)

5tn 360 excavator 3tn swivel dumper with Large Welfare unit Various small tools Water bowser Fuel bowser Vac Ex

Record any visitors

Record and accidents and learning events such as near misses (brief only)

| Signature | Print name |
| --- | --- |
|  | D Tugwell |

Gas feed & main

Planned route for drainage pipe

Planned location for chamber

Electric cable

Gas main and feed

Potential location for chamber

Surface water pipe

Distance of assumed gas main

Depth of water main

Excavation for chamber and new gully

Trying to locate area for chamber

Proposed works